## Sheet1
Honours Project Gantt Chart			Start Date	01/11/20		Notes:	Expecting that if time needs to be made up I will trying to do more in each sprint to lower the total number of them
			End Date	27/4/21

				Ethics/risk forms 27th								Mid-term report 29th					27th final
	November				December				January				February				March				April
	W1	W2	W3	W4	W1	W2	W3	W4	W1	W2	W3	W4	W1	W2	W3	W4	W1	W2	W3	W4	W1	W2	W3	W4
Planning
Write up primary objectives
Initial research into technology
Mock up of initial design/features (UI)
Literature research/review
Other Products research/review
Write up survey
Midterm Report Write Up
Gathering Data
Send
Gather
Review/write up
Sprint Prep
Create Official Backlog
Plan out sprints
Code
Sprint 1
Sprint 2
Sprint 3
Sprint 4
Sprint 5
Sprint 6
Sprint 7
Sprint 8
Review
Overall Testing
User Feedback
Final Report *

*will be written up as the project is done but during this time it will be finalized/finished off